## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | Task Management
1.1 | As a partner I should be able to post a description of a task/project | 3 | Walid Ahmed | Hazem | Ahmed Halawa
1.2 | As a Partner I should identify task/project set of attributes so the admin can check it and the member knows the required skills to apply for it | 3 | Walid Ahmed | Hazem | Ahmed Halawa
1.2 | As a Partner I should add extra attributes to the task/project based on the category so the description of task could be clearer | 3 | Mohammed Ibrahim | Youssef Medhat | Ahmed Ragab
1.8 | As an (Admin) I should be able check the description of a task/project and negotiate with the partner so both partner and admin agree on a description | 5 | Ahmed Ragab | Youssef Medhat | Mohammed Ibrahim
1.9 | As an (Admin) I should be able check the description of a task/project so that I can post it for the members to apply | 5 | Ahmed Ragab | Youssef Medhat | Mohammed Ibrahim
1.9 | As an Admin I should identify task/project set of attributes so the admin can check it and the member knows the required skills to apply for it | 3 | Mohammed Ibrahim | Ahmed Ragab | Youssef Medhat
1.1 | As an Admin I should add extra attributes to the task/project based on the category so the description of task could be clearer | 5 | Youssef Medhat | Ahmed Ragab | Mohammed Ibrahim
1.11 | As an admin I should be able to check who will be assigned to the task based on the applications so that I can decide who gets the job | 5 | Youssef Medhat | Ahmed Ragab | Mohammed Ibrahim
1.12 | As a member I should be able to view tasks so that I can see the requirements to apply | 3 | Ahmed Halawa | Hazem | Walid
1.13 | As a (member) I should be able to search tasks so I can find the description | 8 | Hazem Ashraf | Ahmed Halawa | Walid
1.14 | As a (member) I should be able to apply for tasks so that I can get the job | 5 | Hazem Ashraf | Ahmed Halawa | Walid
1.15 | As a (member) I should be notified when I am accepted so that I can start working on the task | 5 | Ahmed Halawa | Hazem | Walid
1.16 | As a member I should receive a task/project orientation invitation when I am accepted so that I can attend | 5 | Ahmed Halawa | Hazem | Walid
2 | life coach
2.1 | As a (Life Coach) I should be able to post my weekly schedule so members can view it. | 3 | Abdullah | Omar | Ahmed Emad
2.2 | As a (Life Coach) I should be able to confirm booking of a member so that he can view my schedule | 5 | Abdullah | Omar | Ahmed Emad
2.3 | As a (Life Coach) I should be able to receive a notification that a certain time slot was booked so that I can confirm it | 5 | Karim Fekry | Ahmed Emad | Omar
2.4 | As a life coach I should be able to suggest a location with a member so that we can meet | 5 | Karim Fekry | Ahmed Emad | Omar
2.5 | As a life coach/member I should be able to receive a notification confirming the approved booking with both sides so that we can meet | 5 | Omar | Abdullah | Karim Fekry
2.6 | As a member I should be able to book appointments with a life coach so that I can see his schedule | 5 | Omar | Abdullah | Karim Fekry
2.7 | As a member I should be able to suggest a location with a life coach so that we can meet | 5 | Ahmed Emad | Karim Fekry | Abdullah
2.8 | As a member I should be able to view the booked/free/confirmed slots on the system so I can decide the slot I want | 5 | Ahmed Emad | Karim Fekry | Abdullah