## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | Task Management
1.1 | As a partner I should be able to post a description of a task/project | 5 | Walid Ahmed | Hazem Ashraf | Ahmed Ragab
1.2 | As an (Admin) I should be able check the description of a task/project and negotiate with the partner so both partner and admin agree on a description | 3 | Ahmed Ragab | Mohammed Ibrahim | Youssef Medhat
1.3 | As an (Admin) I should be able check the description of a task/project so that I can post it for the members to apply | 3 | Ahmed Ragab | Ahmed Halawa | Mohammed Ibrahim
1.4 | As a/an Partner/Admin I should identify task/project set of attributes so the admin can check it and the member knows the required skills to apply for it | 5 | Mohammed Ibrahim | Youssef Medhat | Ahmed Ragab
1.5 | As a member I should be able to view tasks so that I can see the requirements to apply | 3 | Ahmed Halawa | Hazem Ashraf | Walid Ahmed
1.6 | As a (member) I should be able to apply for tasks so that I can get the job | 3 | Hazem Ashraf | Ahmed Halawa | Youssef Medhat
1.7 | As a (member) I should be able to search tasks so I can find the description | 8 | Hazem Ashraf | Ahmed Halawa | Ahmed Ragab
1.8 | As an admin I should be able to check who will be assigned to the task based on the applications so that I can decide who gets the job | 5 | Youssef Medhat | Walid Ahmed | Hazem Ashraf
1.9 | As a (member) I should be notified when I am accepted so that I can start working on the task | 3 | Ahmed Halawa
2
2.1 | As a (Life Coach) I should be able to post my weekly schedule so members can view it | 5 | Abdullah | Omar | Ahemd Emad
2.2 | As a member I should be able to book appointments with a life coach so that I can see his schedule | 5 | Omar | Abdullah | Karim
2.3 | As a member I should be able to suggest a location with a life coach so that we can meet | 5 | Ahmed Emad | Omar | Karim
2.4 | As a life coach I should be able to suggest a location with a member so that we can meet | 5 | Karim Fekry | Ahmed Emad | Abdullah