## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | Task Management
1.1 | As a member (Admin) I should be able to post a task/project for candidates to apply after negotiation | 5 | Ahmed Ragab | 1.2 | As an admin/partner I should be able to set attributes and then post task/project
1.2 | As a member (Admin/partner) I should be able to set the attributes of the task/project | 5 | Mohamed Ibrahim | 1.5
1.3 | As a member (Admin) I should be able to decide who will be assigned to a task/project based on the application | 5 | Youssef Medhat | 1.1
1.4 | As a member (Candidate) I should be notified when I am accepted | 3 | Ahmed Halawa
1.5 | As a partner I should be able to post a description of a task/project | 5 | Walid Ahmed
1.6 | As a member (Admin) I should be able check the description of a task/project with the partner | 5 | Youssef Medhat
2 | Life Coaching
2.1 | As a member I should be able to suggest a location between life coach and member | 5 | Ahmed Emad
2.2 | As a member (Life Coach) I should be able to confirm booking | 3 | Hazem Ashraf | 2.3
2.3 | As a member I should be able to book appointments | 5 | Omar Mahmoud
2.4 | As a member I should be able to confirm the suggested location | 3 | Karim Khaled Fekry | 2.1
2.5 | As a member (Life Coach) I should be able to post my weekly schedule | 3 | Abdullah Mahmoud